## User Stories
Agile User Story Template
User Story ID | As a <type of user> | I want to <perform some task> | so that I can <achieve some goal> | Sprint | Priority
US-01 | As a User | I want to register as a farmer or buyer | so that I can access the Assured Contract Farming System | Sprint 1 | High
US-02 | As a User | I want to login to the system | so that I can access my account and use platform features | Sprint 1 | High
US-03 | As a User | I want to logout securely | so that I can end my session safely and protect my account | Sprint 1 | Medium
US-04 | As a Farmer | I want to create a farming profile | so that I can showcase my farm details to potential buyers | Sprint 2 | High
US-05 | As a Farmer | I want to update my farming profile | so that I can keep my farm information accurate and current | Sprint 2 | High
US-06 | As a Farmer | I want to add my bank details | so that I can receive payments for farming contracts | Sprint 2 | Medium
US-07 | As a Farmer | I want to add a crop listing to the marketplace | so that I can attract buyers and receive contract offers | Sprint 3 | High
US-08 | As a Buyer | I want to view available crop listings | so that I can identify farming opportunities and potential partners | Sprint 3 | High
US-09 | As a Buyer | I want to search for farmers by crop or location | so that I can find the most suitable farming partners for my needs | Sprint 4 | High
US-10 | As a Buyer | I want to view a farmer's profile | so that I can evaluate their experience and offerings before contracting | Sprint 4 | High
US-11 | As a Buyer | I want to create a purchase contract with a farmer | so that I can formalise the agreement and secure the crop supply | Sprint 4 | High
US-12 | As a User | I want to view all my contracts | so that I can track and manage my active and past agreements | Sprint 4 | Medium
US-13 | As a User | I want to generate system reports | so that I can analyse contract activity and platform usage | Sprint 5 | Medium
US-14 | As a User | I want to send a support request | so that I can get help resolving issues with the platform | Sprint 5 | Medium