## Sprint 1
Sprint Backlog — Sprint 1: Authentication and User Management
Backlog Item | Story Points | Responsible | Status | Original Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Sprint Review
US-01 — User Registration | 5
Design registration form (RegistrationUI) |  | UI Dev | Done | 3 | 3 | 0 | 0 | 0 | 0 | 0
Implement RegistrationController |  | Backend Dev | Done | 3 | 0 | 3 | 0 | 0 | 0 | 0
Implement AuthService password encryption |  | Backend Dev | Done | 2 | 0 | 2 | 0 | 0 | 0 | 0
Implement UserRepository saveUser |  | Backend Dev | Done | 2 | 0 | 0 | 2 | 0 | 0 | 0
Unit tests — registration flow |  | QA | Done | 2 | 0 | 0 | 2 | 0 | 0 | 0
US-02 — User Login | 3
Design login form (LoginUI) |  | UI Dev | Done | 2 | 2 | 0 | 0 | 0 | 0 | 0
Implement LoginController |  | Backend Dev | Done | 2 | 0 | 2 | 0 | 0 | 0 | 0
Implement session token generation |  | Backend Dev | Done | 2 | 0 | 0 | 2 | 0 | 0 | 0
Unit tests — login flow |  | QA | Done | 1 | 0 | 0 | 1 | 0 | 0 | 0
US-03 — User Logout | 2
Implement LogoutController |  | Backend Dev | Done | 1 | 0 | 0 | 1 | 0 | 0 | 0
Implement token invalidation |  | Backend Dev | Done | 1 | 0 | 0 | 0 | 1 | 0 | 0
Unit tests — logout flow |  | QA | Done | 1 | 0 | 0 | 0 | 1 | 0 | 0
Total |  |  |  | 22 | 5 | 7 | 8 | 2 | 0 | 0

## Sprint 2
Sprint Backlog — Sprint 2: Farmer Profile and Payment Details
Backlog Item | Story Points | Responsible | Status | Original Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Sprint Review
US-04 — Create Farmer Profile | 5
Design profile creation form (FarmerProfileUI) |  | UI Dev | Done | 3 | 3 | 0 | 0 | 0 | 0 | 0
Implement ProfileController |  | Backend Dev | Done | 3 | 0 | 3 | 0 | 0 | 0 | 0
Implement FarmerService createFarmerProfile |  | Backend Dev | Done | 2 | 0 | 2 | 0 | 0 | 0 | 0
Implement ProfileRepository saveProfile |  | Backend Dev | Done | 2 | 0 | 0 | 2 | 0 | 0 | 0
Unit tests — create profile |  | QA | Done | 2 | 0 | 0 | 2 | 0 | 0 | 0
US-05 — Update Farmer Profile | 3
Design profile update form |  | UI Dev | Done | 2 | 0 | 0 | 2 | 0 | 0 | 0
Implement FarmerService updateFarmerProfile |  | Backend Dev | Done | 2 | 0 | 0 | 0 | 2 | 0 | 0
Implement ProfileRepository update |  | Backend Dev | Done | 2 | 0 | 0 | 0 | 2 | 0 | 0
Unit tests — update profile |  | QA | Done | 1 | 0 | 0 | 0 | 1 | 0 | 0
US-06 — Add Payment Details | 5
Design payment details form |  | UI Dev | Done | 2 | 0 | 0 | 0 | 2 | 0 | 0
Implement PaymentController |  | Backend Dev | Done | 3 | 0 | 0 | 0 | 3 | 0 | 0
Implement PaymentService validatePayment |  | Backend Dev | Done | 2 | 0 | 0 | 0 | 0 | 2 | 0
Implement PaymentRepository savePayment |  | Backend Dev | Done | 2 | 0 | 0 | 0 | 0 | 2 | 0
Unit tests — payment details |  | QA | Done | 2 | 0 | 0 | 0 | 0 | 2 | 0
Total |  |  |  | 30 | 3 | 5 | 6 | 10 | 6 | 0

## Sprint 3
Sprint Backlog — Sprint 3: Marketplace
Backlog Item | Story Points | Responsible | Status | Original Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Sprint Review
US-07 — Add Product Listing | 5
Design product listing form (MarketplaceUI) |  | UI Dev | Done | 3 | 3 | 0 | 0 | 0 | 0 | 0
Implement ProductController submitProduct |  | Backend Dev | Done | 3 | 0 | 3 | 0 | 0 | 0 | 0
Implement ProductRepository saveProduct |  | Backend Dev | Done | 2 | 0 | 2 | 0 | 0 | 0 | 0
Implement listing validation logic |  | Backend Dev | Done | 2 | 0 | 0 | 2 | 0 | 0 | 0
Unit tests — product listing |  | QA | Done | 2 | 0 | 0 | 0 | 2 | 0 | 0
US-08 — View Marketplace | 3
Design marketplace listing page |  | UI Dev | Done | 3 | 0 | 3 | 0 | 0 | 0 | 0
Implement fetchAllActiveListings |  | Backend Dev | Done | 2 | 0 | 0 | 2 | 0 | 0 | 0
Implement empty state handling |  | Backend Dev | Done | 1 | 0 | 0 | 0 | 1 | 0 | 0
Unit tests — marketplace view |  | QA | Done | 2 | 0 | 0 | 0 | 0 | 2 | 0
Total |  |  |  | 20 | 3 | 8 | 4 | 3 | 2 | 0

## Sprint 4
Sprint Backlog — Sprint 4: Search, Profiles and Contracts
Backlog Item | Story Points | Responsible | Status | Original Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Sprint Review
US-09 — Search Farmers | 5
Design search UI |  | UI Dev | Done | 2 | 2 | 0 | 0 | 0 | 0 | 0
Implement SearchService searchByCrop |  | Backend Dev | Done | 3 | 0 | 3 | 0 | 0 | 0 | 0
Implement SearchService searchByLocation |  | Backend Dev | Done | 2 | 0 | 0 | 2 | 0 | 0 | 0
Unit tests — search |  | QA | Done | 2 | 0 | 0 | 2 | 0 | 0 | 0
US-10 — View Farmer Profile | 3
Design farmer profile view |  | UI Dev | Done | 2 | 0 | 0 | 0 | 2 | 0 | 0
Implement ProfileRepository fetchProfile |  | Backend Dev | Done | 2 | 0 | 0 | 0 | 2 | 0 | 0
Unit tests — view profile |  | QA | Done | 1 | 0 | 0 | 0 | 1 | 0 | 0
US-11 — Create Contract | 8
Design contract creation form (ContractUI) |  | UI Dev | Done | 3 | 0 | 0 | 0 | 0 | 3 | 0
Implement ContractService createContract |  | Backend Dev | Done | 4 | 0 | 0 | 0 | 0 | 4 | 0
Implement contract validation logic |  | Backend Dev | Done | 3 | 0 | 0 | 0 | 0 | 3 | 0
Implement contract notifications |  | Backend Dev | Done | 2 | 0 | 0 | 0 | 0 | 2 | 0
Unit tests — contract creation |  | QA | Done | 3 | 0 | 0 | 0 | 0 | 3 | 0
US-12 — View Contracts | 3
Design contracts list UI |  | UI Dev | Done | 2 | 0 | 0 | 0 | 0 | 0 | 2
Implement ContractService getContracts |  | Backend Dev | Done | 2 | 0 | 0 | 0 | 0 | 0 | 2
Unit tests — view contracts |  | QA | Done | 1 | 0 | 0 | 0 | 0 | 0 | 1
Total |  |  |  | 34 | 2 | 3 | 4 | 5 | 15 | 5

## Sprint 5
Sprint Backlog — Sprint 5: Reports and Support
Backlog Item | Story Points | Responsible | Status | Original Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Sprint Review
US-13 — Generate Reports | 5
Design report selection UI (ReportUI) |  | UI Dev | Done | 2 | 2 | 0 | 0 | 0 | 0 | 0
Implement ReportController |  | Backend Dev | Done | 3 | 0 | 3 | 0 | 0 | 0 | 0
Implement ReportService compileData |  | Backend Dev | Done | 3 | 0 | 0 | 3 | 0 | 0 | 0
Implement PDF/CSV export |  | Backend Dev | Done | 2 | 0 | 0 | 0 | 2 | 0 | 0
Unit tests — reports |  | QA | Done | 2 | 0 | 0 | 0 | 0 | 2 | 0
US-14 — Contact Support | 3
Design support form (SupportUI) |  | UI Dev | Done | 2 | 0 | 0 | 0 | 2 | 0 | 0
Implement SupportController |  | Backend Dev | Done | 2 | 0 | 0 | 0 | 0 | 2 | 0
Implement SupportService createTicket |  | Backend Dev | Done | 2 | 0 | 0 | 0 | 0 | 2 | 0
Implement notifyUser |  | Backend Dev | Done | 1 | 0 | 0 | 0 | 0 | 1 | 0
Unit tests — support |  | QA | Done | 2 | 0 | 0 | 0 | 0 | 0 | 2
Total |  |  |  | 21 | 2 | 3 | 3 | 4 | 7 | 2